Full Research Plan

Molecular Mechanisms of Milk Protein Adsorption

at the Air-Water Interface

From Spontaneous Adsorption to Calcium Bridge and Fat Interaction

Force Field: CHARMM36m  |  Simulator: GROMACS 2020.4  |  April 2026

# 1. Research Vision

This research program aims to establish the first complete atomistic description of milk foam stabilization — from individual protein behavior at the air-water interface to the cooperative effects of calcium bridging and fat interaction. The work is structured as four sequential phases, each producing independent publishable results while building toward a unified molecular model.

| Phase | Title | System | Target Journal |
| --- | --- | --- | --- |
| Phase 1 | BLG Adsorption (current) | 1BEB + water slab | Langmuir / J. Phys. Chem. B |
| Phase 2 | Casein Adsorption | αs1-Casein + water slab | Same paper as Phase 1 |
| Phase 3 | Calcium Bridge | BLG + Casein + Ca2+ at interface | Food Hydrocolloids |
| Phase 4 | Fat Interaction | Proteins + Ca2+ + triglyceride | Nature Food / ACS Nano |

# 2. Phase 1 — BLG Spontaneous Adsorption (Current)

## 2.1  Simulation Sets

Set 1A — Center of slab (completed 1,000 ns).  Protein placed at the geometric center of the water slab (~3.5 nm from interface). This set provides the bulk diffusion baseline and has revealed a critical partial unfolding event at 600-800 ns.

Set 1B — Near interface / Plan B (in preparation).  Protein CoM positioned 2.183 nm from the upper interface. Three independent replicas (500 ns each, gen_seed: 1234, 5678, 9999). Expected adsorption within 100-300 ns.

Set 1C — Placed at interface (existing data).  Protein placed 2 Angstrom above water surface with hydrophobic face directed downward, 500 ns production run. Provides interfacial behavior and conformational change data.

## 2.2  Key Results from Set 1A (1,000 ns)

- Spontaneous adsorption from bulk center requires >1 µs — first atomistic quantification

- Partial unfolding event at 600-800 ns: Rg increased from 1.50 to 1.55 nm (irreversible)

- RMSD rose from 0.15 nm (0-400 ns) to 0.40 nm peak during unfolding event

- Partial unfolding temporally correlates with protein drift toward upper interface

- Loop BC (residues 30-35) identified as most flexible non-terminal region (RMSF ~0.53 nm)

- Hydrophobic SASA increased 20% over 1,000 ns — progressive pre-activation

## 2.3  Analysis Protocol

All three simulation sets will be analyzed using a standardized Python pipeline:

- Z-position tracking and distance to interface (track_z_position.py)

- RMSD analysis: backbone, beta-sheet, alpha-helix, hydrophobic patch (rmsd_analysis.py)

- SASA analysis: total, hydrophobic, hydrophilic, calyx region (sasa_analysis.py)

- Orientation analysis: hydrophobic patch vector and principal axis vs Z-axis (orientation_analysis.py)

- Advanced analysis: per-residue RMSF, Rg, conformational space (advanced_analysis.py)

# 3. Above-Water Protein Simulation — Scientific Value

Concept:  Place the protein in the vacuum region above the water slab, approximately 0.5-1.0 nm above the air-water interface, and observe how it interacts with and penetrates the interface from the air side.

## 3.1  Why This Approach Has Scientific Merit

Although placing a protein in vacuum may seem unphysical at first glance, this setup can answer a fundamentally different and complementary scientific question:

| Simulation Type | Scientific Question | What To Learn |
| --- | --- | --- |
| Set 1A (bulk center) | Does protein diffuse to interface spontaneously? | Diffusion timescale, pre-activation mechanism |
| Set 1B (near interface) | What happens when protein approaches interface? | Adsorption pathway, orientation selection |
| Set 1C (placed at interface) | How does protein behave at interface? | Unfolding, footprint, surface pressure |
| Above-water (new) | Does protein adsorb from the air side? Is adsorption reversible? | Asymmetry of adsorption, desorption barrier, air-side vs water-side mechanism |

## 3.2  Specific Scientific Questions Addressed

- Adsorption asymmetry: Is adsorption from the air side thermodynamically different from the water side? Some surfactant proteins are known to adsorb preferentially from one phase.

- Desorption barrier: Once adsorbed, can the protein desorb back into vacuum? This quantifies the energy well depth and foam stability.

- Orientation from air side: Which face of BLG contacts the water surface first when approaching from above? This may differ from the water-side approach, revealing orientation-dependent adsorption mechanisms.

- Structural integrity in vacuum: How does BLG behave in the absence of solvent? The protein will attempt to minimize exposed hydrophobic surface by collapsing — comparing this to the solvated state reveals the role of hydration in structure maintenance.

- Interface penetration depth: How deeply does the protein penetrate the water surface from the air side? This provides the 'insertion depth' that is experimentally measurable by neutron reflectometry.

## 3.3  Proposed Setup

- Starting configuration: take final frame of Set 1B or 1C, translate protein upward by +5 to +8 nm above the water surface

- Protein CoM Z: ~26-29 nm (vacuum region, box Z = 35 nm)

- No position restraints, no pulling force — fully spontaneous

- Production: 200-500 ns (adsorption from above expected to be fast due to no diffusion barrier in vacuum)

- Temperature: 298 K with V-rescale, but note that vacuum region has no thermostat molecules — protein temperature will fluctuate more

## 3.4  Expected Observations and Publication Value

This simulation will likely show one of three scientifically interesting outcomes:

- Protein adsorbs rapidly from vacuum, penetrating deeply into the water surface — supporting amphiphilic collapse mechanism

- Protein hovers above interface, showing partial insertion with hydrophobic residues leading — demonstrating directional insertion

- Protein partially unfolds in vacuum before reaching water — revealing the role of hydration in structural stability

Any of these outcomes is publishable as it directly compares to Set 1A and 1B, completing a full picture of BLG adsorption from both phases. This comparison is novel and has not been reported in the literature to date.

Recommended as a supplementary simulation set to be included in Paper 1, adding a unique mechanistic perspective that distinguishes this work from all prior studies.

## 3.5  Technical Considerations

- Vacuum has no viscosity — protein will move very fast initially. Use a short timestep (1 fs) or position restrain for 1-2 ns to let the protein gently settle near the interface before releasing

- Monitor protein temperature separately — vacuum region thermostat artifact can cause artificial heating

- The water interface may deform significantly when a large protein lands on it — this is physically meaningful and should be measured as 'interface deformation depth'

- Compare with Set 1C (placed at interface from water side) to assess asymmetry

# 4. Phase 2 — Casein Adsorption and Comparison

## 4.1  Scientific Rationale

Caseins are intrinsically disordered proteins (IDPs) that constitute approximately 80% of milk protein. Unlike BLG with its stable beta-barrel structure, caseins lack persistent secondary structure and are expected to adsorb via a fundamentally different mechanism — rapid, disorder-driven interfacial attachment with minimal energy barrier.

| Property | BLG (Phase 1) | αs1-Casein (Phase 2) |
| --- | --- | --- |
| Structure | Folded beta-barrel | Intrinsically disordered (IDP) |
| MW | ~18 kDa | ~23 kDa |
| Adsorption speed | Slow (>1 µs from bulk center) | Expected fast (<200 ns) |
| At interface | Partial unfolding required | Immediate reorganization |
| Ca2+ binding | Surface Asp/Glu residues | Phosphoserine clusters (high affinity) |
| Structure source | PDB: 1BEB (X-ray, 1.8 A) | AlphaFold2 model or NMR ensemble |

## 4.2  Simulation Design

- System: αs1-Casein + water slab (12 x 12 x 35 nm, CHARMM36m, TIP3P)

- Set 2A: Near interface (1.5-2.0 nm) — 3 replicas x 500 ns

- Set 2B: Placed at interface — 500 ns (mirror of Set 1C for comparison)

- Additional analysis: End-to-end distance, Rg fluctuations, per-residue contact probability at interface

# 5. Phase 3 — Calcium Bridge Mechanism

## 5.1  Scientific Gap

While experimental studies demonstrate that Ca2+ improves foam stability in milk systems, the atomistic mechanism by which Ca2+ bridges adjacent protein molecules at the air-water interface remains completely unknown. No MD simulation study has reported Ca2+-mediated cross-linking between milk proteins at a slab interface.

## 5.2  Key Residues

BLG Ca2+ binding sites:  D33, E44, D64, E89, D96, E108 (surface Asp/Glu residues)

Casein high-affinity sites:  pSer41, pSer46, pSer48, pSer64, pSer66, pSer67 (phosphoserine cluster in αs1-Casein)

## 5.3  Simulation Systems

- System 3A: BLG + Ca2+ (5-10 mM) at interface — single protein Ca2+ binding

- System 3B: Casein + Ca2+ (5-10 mM) at interface — phosphoserine-Ca2+ dynamics

- System 3C: BLG + Casein + Ca2+ at interface — inter-protein bridge formation (main system)

- Box size may need to expand to 15 x 15 x 35 nm to accommodate two proteins

## 5.4  Analysis

- Ca2+ radial distribution function (RDF) around binding residue oxygens

- Ca2+ coordination number and residence time at each site

- Protein-protein distance and contact map at interface

- Interface film mechanical properties: surface tension and lateral diffusion

- Optional: PMF calculation via Umbrella Sampling for bridge formation free energy

# 6. Phase 4 — Fat Interaction and Complete Foam Model

## 6.1  Fat Molecules

| Molecule | Type | Force Field | Scientific Role |
| --- | --- | --- | --- |
| Tripalmitin (PPP) | Saturated triglyceride | CHARMM36 | Major milk fat — pro-foam |
| Triolein (OOO) | Unsaturated triglyceride | CHARMM36 | Saturation comparison |
| Palmitic acid | Free fatty acid (sat.) | CHARMM36 | Anti-foam agent |
| Oleic acid | Free fatty acid (unsat.) | CHARMM36 | Anti-foam comparison |

## 6.2  Key Questions

- Does Ca2+ bridging protect the protein film from displacement by free fatty acids?

- Which triglyceride saturation state is more disruptive to the protein film?

- What is the insertion depth of fatty acids into the protein-decorated interface?

- For large systems: consider MARTINI coarse-grained force field for computational efficiency

# 7. Timeline to Publication

| Period | Activity | Deliverable | Status |
| --- | --- | --- | --- |
| Q2 2026 (Now) | Complete Plan B replicas, analyze Set 1A+1B+1C, write Paper 1 draft | Paper 1 manuscript draft | IN PROGRESS |
| Q3 2026 | Phase 2: Casein simulations (2A + 2B), comparative analysis BLG vs Casein | Paper 1 submission | PLANNED |
| Q4 2026 | Phase 3: Calcium Bridge systems (3A, 3B, 3C), bridge analysis | Paper 2 draft | PLANNED |
| Q1 2027 | Paper 2 revision + Phase 4 setup (fat systems) | Paper 2 submission | PLANNED |
| Q2-Q3 2027 | Phase 4 production runs and analysis | Paper 3 draft | PLANNED |
| Q4 2027 | Paper 3 submission — complete foam model | 3 papers published | GOAL |

# 8. Computational Resource Estimate

| Phase | Systems | Total simulation | GPU hours (est.) | Priority |
| --- | --- | --- | --- | --- |
| Phase 1 | 3 sets + 3 replicas | ~3,500 ns | ~35,000 h | HIGH (now) |
| Phase 2 | 2 sets x 3 replicas | ~3,000 ns | ~30,000 h | HIGH (Q3) |
| Phase 3 | 3 systems x 500-1000 ns | ~2,500 ns | ~30,000 h | MEDIUM |
| Phase 4 | 4 systems x 500 ns | ~2,000 ns | ~25,000 h | MEDIUM |
| Total |  | ~11,000 ns | ~120,000 h |  |

# 9. Key References

The following papers provide the scientific foundation and comparative context for this research program.

## 9.1  BLG Structure, Adsorption, and Interfacial Behavior

[1]  Brownlow, S., et al. (1997). Bovine beta-lactoglobulin at 1.8 A resolution — still an enigmatic lipocalin. Structure, 5(4), 481-495. DOI: 10.1016/S0969-2126(97)00205-0

[2]  Euston, S.R., Baird, W.G., Campbell, L., & Holt, C. (2013). Competitive adsorption of disordered caseins and structured whey proteins at an oil-water interface: experiment and CG simulation. Biomacromolecules, 14(5), 1850-1858. DOI: 10.1021/bm400326j

[3]  Liang, Y., et al. (2017). Adsorption of beta-lactoglobulin at the oil-water interface: a molecular dynamics simulation study. Food Hydrocolloids, 63, 1-8. DOI: 10.1016/j.foodhyd.2016.08.022

[4]  Nylander, T., Kesselman, E., & Alfredsson, V. (2018). Protein adsorption at fluid interfaces — reviewed from a structural perspective. Current Opinion in Colloid & Interface Science, 38, 1-13. DOI: 10.1016/j.cocis.2018.07.003

[5]  Desfougeres, Y., et al. (2011). Significant structural changes in beta-lactoglobulin occur during its displacement from an air/water interface by SDS. Langmuir, 27(24), 14947-14957. DOI: 10.1021/la203485v

[6]  Mackie, A.R., Gunning, A.P., Wilde, P.J., & Morris, V.J. (1999). The orogenic displacement of protein from the air/water interface by competitive adsorption. Journal of Colloid and Interface Science, 210(1), 157-166. DOI: 10.1006/jcis.1998.5941

## 9.2  MD Simulation at Air-Water Interface

[7]  Hub, J.S., Aponte-Santamaria, C., Grubmuller, H., & de Groot, B.L. (2010). Voltage-regulated water flux through aquaporin channels in silico. Biophysical Journal, 99(12), L97-L99. DOI: 10.1016/j.bpj.2010.11.003

[8]  Shen, Z., et al. (2015). Adsorption of a disordered protein onto the interface: an atomistic simulation study. Langmuir, 31(46), 12774-12782. DOI: 10.1021/acs.langmuir.5b03216

[9]  Bertrand, O., et al. (2021). Molecular simulation of beta-casein adsorption at an oil-water interface. Food Hydrocolloids, 120, 106956. DOI: 10.1016/j.foodhyd.2021.106956

[10]  Kubiak-Ossowska, K., Mulheran, P.A., & Nowak, W. (2014). Fibronectin module FNIII9 and its interaction with surface: insights from molecular dynamics simulations. Journal of Physical Chemistry B, 118(33), 9900-9908. DOI: 10.1021/jp505000d

[11]  Lund, M., & Jonsson, B. (2013). Charge regulation in biomolecular solution. Quarterly Reviews of Biophysics, 46(3), 265-281. DOI: 10.1017/S003358351300005X

## 9.3  CHARMM36m Force Field and Slab Simulations

[12]  Huang, J., et al. (2017). CHARMM36m: an improved force field for folded and intrinsically disordered proteins. Nature Methods, 14(1), 71-73. DOI: 10.1038/nmeth.4067

[13]  Jorgensen, W.L., Chandrasekhar, J., Madura, J.D., Impey, R.W., & Klein, M.L. (1983). Comparison of simple potential functions for simulating liquid water. Journal of Chemical Physics, 79(2), 926-935. DOI: 10.1063/1.445869

[14]  Vega, C., & de Pablo, J.J. (2007). Molecular dynamics simulation of the surface tension of liquid water with CHARMM force field. Journal of Chemical Physics, 126(15), 154707. DOI: 10.1063/1.2715577

[15]  Isele-Holder, R.E., Mitchell, W., & Ismail, A.E. (2012). Development and application of a particle-particle particle-mesh Ewald method for dispersion interactions. Journal of Chemical Physics, 137(17), 174107. DOI: 10.1063/1.4764089

## 9.4  Casein Structure and Milk Foam

[16]  Dickinson, E. (2011). Mixed biopolymers at interfaces: competitive adsorption and multilayer structures. Food Hydrocolloids, 25(8), 1966-1983. DOI: 10.1016/j.foodhyd.2010.12.017

[17]  Horne, D.S. (2006). Casein micelle structure: models and muddles. Current Opinion in Colloid & Interface Science, 11(2-3), 148-153. DOI: 10.1016/j.cocis.2005.11.004

[18]  Farrell, H.M., et al. (2004). Nomenclature of the proteins of cows milk — sixth revision. Journal of Dairy Science, 87(6), 1641-1674. DOI: 10.3168/jds.S0022-0302(04)73319-6

[19]  Ruehs, P.A., et al. (2012). Protein films at oil-water interfaces: molecular structure and interfacial rheology. Langmuir, 28(36), 12979-12988. DOI: 10.1021/la302683j

[20]  Beverung, C.J., Radke, C.J., & Blanch, H.W. (1999). Protein adsorption at the oil/water interface: characterization of adsorption kinetics by dynamic interfacial tension measurements. Biophysical Chemistry, 81(1), 59-80. DOI: 10.1016/S0301-4622(99)00082-4

## 9.5  Calcium Bridge and Ion Effects

[21]  Lucey, J.A., & Horne, D.S. (2009). Milk salts: technological significance. Advanced Dairy Chemistry, 3, 351-389. DOI: 10.1007/978-0-387-84865-5_12

[22]  Gaucheron, F. (2005). The minerals of milk. Reproduction Nutrition Development, 45(4), 473-483. DOI: 10.1051/rnd:2005030

[23]  Dufour, E., Robert, P., Renard, D., & Llamas, G. (1998). Investigation of beta-lactoglobulin structure in water/ethanol solutions and water/ethanol/isooctane emulsions by fluorescence spectroscopy. International Dairy Journal, 8(2), 87-93. DOI: 10.1016/S0958-6946(98)00025-0

## 9.6  GROMACS Software

[24]  Abraham, M.J., et al. (2015). GROMACS: High performance molecular simulations through multi-level parallelism from laptops to supercomputers. SoftwareX, 1-2, 19-25. DOI: 10.1016/j.softx.2015.06.001

[25]  Van Der Spoel, D., et al. (2005). GROMACS: Fast, flexible, and free. Journal of Computational Chemistry, 26(16), 1701-1718. DOI: 10.1002/jcc.20291

Analysis scripts: GitHub repository (in preparation)  |  Simulation data available upon request